### HENRY IV PARTS 1 AND 2

Revised Tech Schedule

NOTE: Activities for Both Parts in **Black**, Activities for Part I only in Red, Activities for Part II only in Blue.

*Date Time Personnel Activity (start time)*

## Sound Preview to be scheduled independently by the directors and designers, to be completed by October 18.

Sunday October 16

 11am-12noon HWD, BG, SD, TD, SM Backup time for Lift/Wall heights

12-1 pm HWD, BG, Cast, SM, TD Safety tour of set

1-5 pm BG, Cast, SM On Set Rehearsal- Part I

 *\*\*Marroney Circle of Friends in attendance*

Monday October 17

7-11 pm HWD, Cast, SM On Set Rehearsal- Part II

DAY OFF FOR ALL DESIGNERS AND PRODUCTION AREAS

Tuesday October 18

 4:00 pm HWD, BG, SM, Partial Cast Media Photocall (Parts I and II)

 Costumes, Lights, TD, SD

 7-11 pm BG, Cast, SM, TD On Set Rehearsal- Part I

Wednesday October 19

3-5 pm BG, SM, SD, LD, SND Paper Tech Part I

4-6 pm DJW, Cast, SM Vocal Workshop onstage

6:30-7:00 pm HWD, SM, Cast, Props Gun Safety Training

7-11 pm HWD, Cast, SM, TD On Set Rehearsal- Part II

Thursday October 20

1-3pm Director, SM, SD, LD, SND Paper Tech Part II

3-7 pm Lights Level Set Part I

7:00pm BG, Cast, SM, TD, Crew Call to Theatre

 7:30-11pm All Above Tech Watch- Part I

Friday October 21

 1-5 pm Lights Level Set Part I

 5-6:30 pm Lights Changeover to Part II

7:00pm HWD, Cast, SM, TD, Crew Call to Theatre

 7:30-11pm All Above Tech Watch- Part II

Saturday October 22

 9am-6pm Lights, Sound Level Set Part II

 7-11 pm Lights, Sound Continue Level Set if needed

 DAY OFF FOR ALL ACTORS AND STAGE MANAGEMENT