### HENRY IV PARTS 1 AND 2

Revised Tech Schedule

NOTE:  Activities for Both Parts in Black, Activities for Part I only in Red, Activities for Part II only in Blue.

Date		Time			Personnel				Activity (start time)

## Sound Preview to be scheduled independently by the directors and designers, to be completed by October 18.

Sunday October 16

11am-12noon		HWD, BG, SD, TD, SM		Backup time for Lift/Wall heights

12-1 pm			HWD, BG, Cast, SM, TD		Safety tour of set

1-5 pm			BG, Cast, SM			On Set Rehearsal- Part I

**Marroney Circle of Friends in attendance

Monday October 17

7-11 pm			HWD, Cast, SM			On Set Rehearsal- Part II

DAY OFF FOR ALL DESIGNERS AND PRODUCTION AREAS

Tuesday October 18

4:00 pm			HWD, BG, SM, Partial Cast	Media Photocall (Parts I and II)

Costumes, Lights, TD, SD

7-11 pm			BG, Cast, SM, TD			On Set Rehearsal- Part I

Wednesday October 19

3-5 pm			BG, SM, SD, LD, SND		Paper Tech Part I

4-6 pm			DJW, Cast, SM			Vocal Workshop onstage

6:30-7:00 pm		HWD, SM, Cast, Props		Gun Safety Training

7-11 pm			HWD, Cast, SM, TD		On Set Rehearsal- Part II

Thursday October 20

1-3pm			Director, SM, SD, LD, SND	Paper Tech Part II

3-7 pm			Lights				Level Set Part I

7:00pm			BG, Cast, SM, TD, Crew		Call to Theatre

7:30-11pm		All Above			Tech Watch- Part I

Friday October 21

1-5 pm			Lights				Level Set Part I

5-6:30 pm		Lights				Changeover to Part II

7:00pm			HWD, Cast, SM, TD, Crew		Call to Theatre

7:30-11pm		All Above			Tech Watch- Part II

Saturday October 22

9am-6pm		Lights, Sound			Level Set Part II

7-11 pm			Lights, Sound			Continue Level Set if needed

DAY OFF FOR ALL ACTORS AND STAGE MANAGEMENT